## Sheet1
Gantt Chart for Waterscope Project |  |  | Key | Sajan |  | Aaron |  | Katie |  | Nathan |  | Monica |  | Unassigned/All
Meet with Waterscope team | ? | ? | ?! | ?!? | cry.
Project Proposal
Technical Report
Ideas and Modelling to finalise project focus
Overview, Context and Enginerring Approach
Project Management Plan + Gantt Chart
Strengths/Weaknesses/ source training expertise
Costings + list of parts required
Risk assessment and contingency plan
Short look at Unicef Principles?
Collate/Review and Finalise Project Proposal
Revise Contingency plan in light of feedback
Interim Presentation
Order Parts
Ensure training programs done for respective skills
Write team members' personal and technical development
Complete prototype and check feasibility
Website Design
Prepare Interim Presentaons
Project Presentation/Reports
Decide who is presenting what parts
Start preparing presentation
Collate ideas and feedback with problems and etc
Statement on Unicef Principles/how our project fits
Web Design and completion
Technical Presentation on project
Reflect (Strengths and weaknesses)
Day Number
| M | T | W | T | F |  | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
| 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 |  | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2018-06-03 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07
|  |  |  | Project Proposal |  |  | 2018-05-29: Interim Presentations; 2018-06-06: Project presentations