## Sheet1
Gantt Chart for Waterscope Project |  |  |  | Key | Sajan |  | Aaron |  | Katie |  | Nathan |  | Monica |  | Unassigned/All
Day Number
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
| 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2018-06-03 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07
Meet with Waterscope team | bar: 2018-05-14
Project Proposal | bar: 2018-05-14 to 2018-05-16
Technical Report | bar: 2018-05-14 to 2018-05-15
Ideas and Modelling to finalise project focus | bar: 2018-05-14 to 2018-05-15
Overview, Context and Engineering Approach | bar: 2018-05-14 to 2018-05-15
Project Management Plan + Gantt Chart | bar: 2018-05-14 to 2018-05-15
Strengths/Weaknesses/ source training expertise | bar: 2018-05-14 to 2018-05-15
Costings + list of parts required | bar: 2018-05-14 to 2018-05-15
Risk assessment and contingency plan | bar: 2018-05-14 to 2018-05-15
Collate/Review and Finalise Project Proposal | bar: 2018-05-16
Revise Contingency plan in light of feedback | bar: 2018-05-17
Interim Presentation | bar: 2018-05-17 to 2018-05-29
Short look at Unicef Principles? | bar: 2018-05-17
Order Parts | bar: 2018-05-17 to 2018-05-21
Ensure training programs done for respective skills | bar: 2018-05-17 to 2018-05-24
Complete prototype and check feasibility | bar: 2018-05-17 to 2018-05-29
Website Design | bar: 2018-05-24 to 2018-05-25
Prepare Interim Presentation | bar: 2018-05-25 to 2018-05-29
Prototype development timeline | bar: 2018-05-25 to 2018-05-29
Design development timeline | bar: 2018-05-25 to 2018-05-29
Write team members' personal and technical development | bar: 2018-05-25 to 2018-05-29
Gantt Chart Update and Prokect Management | bar: 2018-05-25 to 2018-05-29
Meet again with Waterscope and collect filters | bar: 2018-05-17 to 2018-05-22
Project Presentation/Reports | bar: 2018-05-29 to 2018-06-06
Decide who is presenting what parts | bar: 2018-05-29 to 2018-05-30
Start preparing presentation | bar: 2018-05-29 to 2018-06-06
Collate ideas and feedback with problems and etc | bar: 2018-05-29 to 2018-06-06
Statement on Unicef Principles/how our project fits | bar: 2018-05-29 to 2018-06-06
Web Design and completion | bar: 2018-05-29 to 2018-06-06
Technical Presentation on project | bar: 2018-05-29 to 2018-06-06
Gantt Chart Update and Prokect Management | bar: 2018-05-29 to 2018-06-06
Reflect (Strengths and weaknesses) | bar: 2018-05-29 to 2018-06-06
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
| 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02 | 2018-06-03 | 2018-06-04 | 2018-06-05 | 2018-06-06 | 2018-06-07
|  |  |  | Project Proposal | [11 empty] | Interim Presentations | [7 empty] | Project presentations